## QA
＃ | Page | Title | Contents | Date of question | Answer | Respondent | Date of answer
e.g. | P6 | Background and basic policy | The Finance area assumes a Fit to standard introduction to S/4HANA Cloud, but considering our school's situation, which would you recommend, RISE or GROW? | 2025-02-01 | We recommend RISE. Because XXXXX | OIST Tancha | 2025-02-02
1 | P.10 | Cut-over timing | At High Level Project Timeline does not describe cut over date. Can we assume the cut over date as "January 2027"? Also does OIST accept to go-live during fiscal year from accounting audit aspect (We assume OIST fiscal year is from April to March)? | 2025-08-20 | Yes. January is OK for Cut-over date. Go-live during fiscal year is OK. And OIST want to avoid the new Fiscal yesr (Apr) as a cut-over date. Cutover and go live is better on december 1st 2026 or earlier, and avoid year end. Fiscal year end is 2027 March but that has to have the buffer and hyper care. | Hakkie Min Okay Cem | 8/21/2025 8/28/2025
2 | P.17 | WalkMe | May I understand what your expectation to WalkMe application? It is supposed that Guidance function could be main expectation. Do you also have idea to introduce Insight and/or other funtions in WalkMe? | 2025-08-20 | Yes. Guidance function is the main fuctioanlity we expect. And it is nice to have; not mandatory. We may be considering to drop it out from the scope of this project. Therefore proposal needs to be itemized and organized for us to see with or without walkme implications. | Hakkie Min Okay Cem | 8/21/2025 8/28/2025
3 | P.17 | Target documents for DMS storage | (1) Can we know what documents will be expected to be storaged in OpenText? (2) What documents the targets of "automation IF(Job, API)" with S/4 HANA? It discribed that OpenText and S/4 HANA will have IF, however, there is no information about the IF in "6. OIST_ToBe System_IF_List_Phase0Assesment.xlsx". | 2025-08-20 | (1) We expect that the documents mainly managed in Procurement process - 契約書, 領収書, 請求書, 納品書, 見積書, 注文書, 検収書等 .. will be sored in OpenText and interfaced with S/4H. We have natual integration between S/4H and OpenText so donlt need additional Interface development. To complete the context, our vision is to move paperless, I would like to see a partner to bing an approach to enable it. please focus on outcome, and bring your expertise, as we will have systems that require connectivity Opentext being one of them, other core interfaces for successfactors, BPO payroll vendor system, concur, asset systems, SAC, etc.. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
4 | P.17 | System scope | There are scope GAP between RFP and appendix. For example, SuccessFactors scope in P.5 "OIST Phase 0 - System landscape strategy_v02.pdf" is different with scope in P.17 "3.OIST-Phase 1 RFP.pdf". We assume RFP is official information for scope of implementation, however could you please identify which business operation, or "OIST Phase 0 - Concept of Operations" is in-scope? | 2025-08-20 | I am sorry for the confusion. THe scope in RFP is the latest information. Please refer to the scope in RFP rather than appendix. Also you can consider On-boarding and Employee data management (EC Central) is the HR scope only. You can cosider the other HR business operations scope in "OIST Phase 0 - Concept of Operations" as out of scope in proposal. | Hakkie Min | 2025-08-21
5 | P.22 | Development target (Report & IF) | It looks that the number of the report objects is different from the totals in "7. OIST_ToBe Report_List_Phase0Assesment.xlsx". The number of the interface as well in "6. OIST_ToBe System_IF_List_Phase0Assesment.xlsx". Can I clarify what is the cause of the differences? | 2025-08-20 | If you mean the gaps between the worksheet of "To-Be Reports List" and "Pivot",, just focus on the "To-Be Reports List" only. Note that these are still assumptions. I do not approve any ABAP unless absolutely necessary and these need to be SAC reports or covered by standard reports. I expect SI to act like it. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
6 | P.22 | Development target (Conversion, Enhancement, Form, and Workflow) | Could you provide the breakdown of the development objects for Conversion, Enhancement, Form, and Workflow? I would like to know which (S/4HANA, SuccessFactors and Concur) is base solution for them to estimate the development effort and resources. | 2025-08-20 | I am sorry we cannot provide much detail breakdown anymore. Just refer to the current contents in appendix Just like previous item, task is to eliminate most of AS-IS based custom objects, any kind of code, user exit, enhancement, form and wprkflow and build a new baseline. Please refer to what has been provided in appending and in RFP as a reference and consider what SAP best practice needs to be and propose as such. One of the aspect of the selection process will be your ability to make us fit the standard. and build onlu necessary worklows, interfaces and maybe forms for it. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
7 | P.29 | Estimation of expenses | Can we state the estimated travel and other project expenses into the category "Other" in "2. Cost Estimation Sheet.xlsx" ? | 2025-08-20 | Yes. You can fill out the T&E in "Other" category. | Hakkie Min | 2025-08-21
8 | P.29 | Cost Estimation | About "2. Cost Estimation Sheet.xlsx" we will fill in "Cost Estimation (BPO)" sheet only. Will not fill in "Cost Estimation (SF EC payroll)" due to decision of outsourcing for payroll process. Please confirm | 2025-08-20 | Sorry for the confusion here. Yes. Please neglect the "Cost Estimation (SF EC payroll)" worksheet. Please estimate the interfaces needed for payroll service, data in & out. Master data needs to go to BPO provider and results needs to come as an accounting document. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
9 | Appendix. 4. Business Process list (as-is) | Business Process List | Could you explain "Business Process List (as-is).xlsx? 1) It seems that the cells from C1 to JU1 are business process, then how about definition of cells from A2 to A366? Are these "application subjects" for each business process? Because cell A1 identifies "Workflow name" please clarify the definition. 2) About cells from A2 to A366 there are suffix existing for some lines, such as "(Done)", "(complete)", "*OLDflow", "*TBC" etc.. Could you please clarify the definition? | 2025-08-21 | 1) The cells from C1 to JU1 are business process list defined by American Accounting insititutes (to be confirmed later) and cells from A2 to A366 are work flow list defined in OIST. 2) The suffix in cells from A2 to A366 such as "(Done)", "(complete)", "*OLDflow", "*TBC" etc. are status of the workflow at that time of preparation of this excel file. So you don't need to concern about it so much, Just understand that OIST managed these list of workflow. I suggest SIs to bring fit to standard mentality and try not to adapt current flows for adjustment, but jump into best practices. these flow should tell you your potential challenges and help you strategize your fit to standard approach. this fit to standard should br best practices mentality, not as in if we can configure with standard config tools it is still standard mentality. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
10 | Appendix.10 P.36~ | Leadership/Influencer's voice | Leadership/Influencer's interview summery helps us understand their ideas. Should we consider them as requirements of Phase1? Or take as potential needs or suggestions to improve our plan and proposal. Ref "10. OIST Phase 0 - Change Strategy_20250521.pdf" | 2025-08-21 | You will have a chance again to interview with them when the project started. But you can consider the interview summary as requirements of Phase1 as their comments will not be so different even you have an interview in implementation project. | Hakkie Min | 2025-08-22
11 | Appendix.10 P.10 | Stakeholder Group | Could you clarify in which stakeholder group Research Unit / Faculty members are included? Also, please provide your thoughts regarding their "Involvement level" (H/M/L). Asking because we assume RU/Faculty members would be significantly influential stakeholders, and want to make sure if this assumption is correct. Ref "10. OIST Phase 0 - Change Strategy_20250521.pdf" | 2025-08-21 | Not all of the Research Unit / Faculty members but some of the supporting team are heavy user of the ERP system in the area of Grant/Budget/Procurement/Travel & Expense/On-boarding/Employee Data management. You will have a chace to interview with its representative and dicsuss on requirements and to be process, so their "Involvement level" should be "HIgh". also condiser this, you are implementing a fit to standard to best practices for finance, procurement and HR modules, you will have access to business process owners who will need to deal with influecing memebers. your job will be supporting and ensuring we will not create a scope scrape and delays in the project. | Hakkie Min Okay Cem | 8/22/2025 8/28/2025
12 | Request for proposal for the renewal of OIST’s ERP system and related applications P36 | Oral Presentation | The main members are planning to visit your university, but would it be possible for some members to participate remotely? | 2025-08-21 | Yes. The project manager must attend in person and deliver the presentation. Other members can participate remotely. | A.Villar | 2025-08-25
13 | RFP - P19 | Data Migration | In the list of migration target, "Customer Master" is not included. We understand that is because OIST is currently not using SD module and there is no Customer Master existing. However, if SD is to be used in future for employee housing (lease) fees, Employee master need to be registered as Customer master and thus, need to be counted as a migration target. Is our understanding correct? | 2025-08-25 | Yes, the understanding is correct. Business Owner will prepare the list, which is currently mixed in our vendor master. One more commnets regarding the SD implementation, if we can meet the requirements with Business Partner and Fi-AR module, we may not need SD implementation as the biz req from OIST on SD is not complex. The main requirements is Billing plan managemnet to Grantor and employee housing (lease) fees. | A. Villar Hakkie Min | 2025-08-25
14 | RFP - P19 | Data Migration | Payroll data is listed in the migration scope. Our understanding is that historical payroll data will be migrated to the BPO system and is not intended to be migrated to SAP SuccessFactors. Could you please confirm if this understanding is correct? We also recognize that payroll data is a topic that needs to be considered across the entire project. | 2025-08-25 | At this moment, we are not considering to migrate historical payroll (payslips) to SAP SuccessFactor. However, please consider the possibility to bring at least master data SAP SF, besides having BPO Payroll. | A.Villar | 2025-08-25
15 | 7. OIST_ToBe Report_List_Phase0Assesment.xlsx No80 | Report List | In the attached file '7. OIST_ToBe Report_List_ Phase0Assessment,' item No. 80 refers to 'SuccessFactors Recruiting.' Since this module is not within the scope of the current proposal, should this report be considered out of scope? | 2025-08-25 | Sorry for the misunderstanding. It is not in the scope of current system. However, please consider that it might be part of the project scope. Reporting area requires further analysis by System Implemnetation vendor and OIST. In some cases it could be tackle with OOB reports, or by using SAC reporting. | A.Villar | 2025-08-25
16 | RFP-P31 | Estimation Assumption | How is the contract structure being considered? Is it expected to be phased, with separate agreements for each stage? The RFP says, 'Provide a detailed estimate for the project support and a detailed or rough estimate for the project and operation and maintenance.' Does this mean that the estimation will be fixed or rough depending on the phase? | 2025-08-25 | Please consider a single contract for the whole contract with specified payment based on deliverables per phase. Separately, please provide the information regarding operation and maintenance. | A.Villar | 2025-08-25
17 | RFP-P28 | Table of Contents Structure and Contents | Both Chapter 2 and Chapter 7 focus on Project Management, and I believe there is some overlap in the content. Would it be better to intentionally keep them as separate chapters? | 2025-08-25 | Chapter 2 refers to methodology and tools that you will use for project management. chapter 7 is focus on your proposed project management for this specific project. | A.Villar | 2025-08-25
18 | RFP-P32 | Support structure and project management methodology | When working onsite, will facilities such as workspace, PC, and network access be available? Also, will amenities like dining facilities be accessible? | 2025-08-25 | Yes, the facilities (space, desk, network access, etc.) will be provided. No PC or displays will be provided, vendor must procure their own equipment. Also, access to cafeteria or other facilities will be granted, as well as IC card for access across campus. Please note that there are no dining facility on campus after 6 pm and conveinence store closes at 8pm. For transportation we do have bus from campus certain limited routes, and we do have parking for guest/rental cars. | A.Villar Okay Cem | 8/25/2025 8/28/2025
19 | RFP-P20 | Data Migration | In preparation for the transition in January 2027, would it be possible to use the year-end and New Year holiday period for data and system migration? | 2025-08-25 | In theory yes. However, please consider that OIST staff avaialability will be limited. Cutover and go live is better on december 1st 2026 or earlier, and avoid year end. | A.Villar Okay Cem | 8/25/2025 8/28/2025
20 | P.17 | SSO Login Assumption | Is it assumed that Single Sign-On (SSO) will be used for login? | 2025-08-25 | Yes, this is correct. IT plans to use Microsoft Azure SSO together with SAP Identity Management. | A.Villar | 2025-08-25
21 | P.17 | Final T&A system | Is it correct to understand that the T&A system has been finalized using King of Time? In the To-Be I/F list, there was the notation KOT or BPO. | 2025-08-25 | At this moment it has not finalized the negotiation with BPO and and scope. Please consider that in the case BPO does not offer T&A application, most likely the project will continue with the assumption of using KOT. | A.Villar | 2025-08-25
22 | P.17 | Details of System scope | To propose an optimal system configuration, could you please share your assumptions regarding the specific usage of MM and SD modules? For example: assumptions about MM being used primarily for indirect material procurement, Inventory Management for laboratory reagents, SD for contract/joint research revenue management, etc. | 2025-08-25 | Although this requires further analysis during technical design. Please use next comments as a reference. ¦ MM Process Area ¦ University Use Case ¦ Linked Modules ¦ ¦ ----------------------------- ¦ ----------------------------------------------------- ¦ ------------------------------- ¦ ¦ **Purchase Requisition (PR)** ¦ Staff/faculty request lab supplies, IT, services ¦ FI/CO, FM, GM ¦ ¦ **RFQ / Quotation** ¦ Collect vendor bids for equipment, services ¦ SD (if revenue contracts exist) ¦ ¦ **Purchase Order (PO)** ¦ Issue POs with approval workflows ¦ FI/CO, FM, GM ¦ ¦ **Goods Receipt (GR)** ¦ Confirm delivery of supplies/equipment ¦ FI-AP, CO ¦ ¦ **Invoice Verification** ¦ 3-way match: PO, GR, Invoice ¦ FI-AP ¦ ¦ **Goods Issue / Consumption** ¦ Issue consumables to labs, workshops ¦ CO, GM ¦ ¦ **Contract Mgmt** ¦ Framework agreements for services/equipment ¦ OpenText ¦ [Not in scope] ¦ **Inventory Mgmt** ¦ Stock for chemicals, IT hardware, consumables ¦ CO ¦ ¦ **Stock Transfer** ¦ Move materials between central stores and departments ¦ CO ¦ [Currently in Bugyo system] ¦ **Physical Inventory** ¦ Annual stock count for compliance (ASBJ rules) ¦ FI, Audit ¦ ¦ SD Process Area ¦ University Use Case ¦ Linked Modules ¦ ¦ ---------------------------- ¦ ----------------------------------------------------------- ¦ --------------------- ¦ ¦ **BP (Business Partner)** ¦ Maintain sponsors, collaborators, funders, external clients ¦ FI, GM ¦ ¦ **Sales Order Mgmt** ¦ External research services, training programs, IP royalties ¦ FI, CO, GM ¦ ¦ **Service Confirmation** ¦ Confirmation of lab services, consulting work ¦ CO ¦ ¦ **Billing** ¦ Generate invoices for services / grants fees ¦ FI-AR, e-Invoicing JP ¦ ¦ **Accounts Receivable (AR)** ¦ Manage balances, payments, dunning ¦ FI ¦ ¦ **Revenue Recognition** ¦ Post revenue to correct accounts (per ASBJ standards) ¦ FI ¦ ¦ **Integration with Grants** ¦ Invoice funding agencies, project sponsors ¦ GM ¦ ¦ **Integration with Bugyo** ¦ Provide data for statutory filings in Japan ¦ FI ¦ | A.Villar | 2025-08-25
23 | P.22 | Request for Additional WRICEF Documentation | Could you please provide detailed specification documents for the items other than Report and Interface (Conversion, Enhancement, Form, and Workflow) in the WRICEF Scope? | 2025-08-25 | At this moment there is no further information on terms of WRICEF Scope. Please consider the definition will come during technical desgn phase. I suggest SIs to bring fit to standard mentality and try not to adapt current flows for adjustment, but jump into best practices. these flow should tell you your potential challenges and help you strategize your fit to standard approach. this fit to standard should br best practices mentality, not as in if we can configure with standard config tools it is still standard mentality. so requirements amd design for mandatory items of RICEF needs to be come from project team during hte project as part of discovery and explore phases aligned with best practices. | A.Villar Okay Cem | 8/25/2025 8/28/2025
24 | - | Bidding procedure | Will this procurement follow formal bidding procedures? If yes, please provide comprehensive details on the required documentation, submission methods, timeline including bidding dates, and all applicable procedural requirements. | 2025-08-25 | This procurement will be conducted as a proposal competition, not as a standard bidding process. The vendor achieving the highest score, based on the Proposal Checksheet (scoring criteria), will be nominated as the candidate for the contract. | Procurement Section | 2025-08-25
25 | - | Training Infrastructure | Can we assume eFront LMS will be used to host, track & report training completions for the purpose of this rollout? | 2025-08-25 | It was not considered in that sense, but it is possible. Please take note that in case of using eFront, the vendor must create the material for the training. Vendor must create training material regardless, and be ready for tracking regardless of methodology of implementation. My preference is that trainings are going to be a classroom format mainly and materials will be used middle hire and new users either as operating manual or eFront hosted or maybe Walk me format. | A.Villar Okay Cem | 8/25/2025 8/28/2025
26 | - | WalkMe | Please share the WalkMe license components that have been or will be purchased 1) Base capabilities: WalkMe Web + Flow Analytics 2) Add-on capabilities: e.g. WalkMe Mobile, Workstation, TeachMe, Predictive Analytics, etc.) | 2025-08-25 | We are only considering base capabilities (WalkMe Web + Flow Analytics) Walk me is nice to have; not mandatory. We may be considering to drop it out from the scope of this project. Therefore proposal needs to be itemized and organized for us to see with or without walkme implications. it is one of the fist thing that i will cut if needed to be. | A.Villar Okay Cem | 8/25/2025 8/28/2025
27 | - | WalkMe | Is SAP Concur license Standard or Premium? With standard Concur license, embedded WalkMe solutions are readily available and cannot be customized. With Premium license, the embedded solutions are customizable. | 2025-08-25 | Please consider SAP Concur license standard. | A.Villar | 2025-08-25
28 | Proposal Checksheet | Clarification on Functional and Technical Aspects in S/4HANA Migration | Could you please clarify what specifically is meant by 'functional and technical aspects' in the context of S/4HANA migration capability? We would appreciate a detailed explanation of what elements or capabilities each of these aspects encompasses. | 2025-08-25 | Functional aspects refer to how business processes are supported and transformed (e.g., finance, HR, procurement, compliance, and user experience), while technical aspects focus on the underlying system enablement (e.g., migration approach, data migration tools, integrations, infrastructure, security, and performance). In short: functional = business process readiness; technical = system and platform readiness. There are point that I request responders not to overthink. you are the experts of how things done, you need to bring that expertise instead of what we are trying you tell you. I except each vendor to have a metgodology and project framework that come with a set of templates and activities and deliverables, which would also have functional and trechnical aspects of many tasks that you should be aware of. | A.Villar Okay Cem | 8/25/2025 8/28/2025
29 | Proposal Checksheet | OIST's Cultural and Working Environment Characteristics | What are the key characteristics of OIST's culture and working environment that vendors should align with in terms of communication styles? | 2025-08-25 | I can say in shortly International community and decentralized organization and process is the key characteristics of OIST's culture. You should consider to interview and communicate with very different styles of role and people during the project - staff, Faculty and research, ... it is a diverse environment, communcation needs to be clear easy to understand and preferably face to face. although personnel may have different opinions they will follow the process, and of course they may ask questions. what they will need is clarity, understanding and guidance. Take this as a guidance: if something is too complicated to explain , then something must be wrong with it. | Hakkie Min Okay Cem | 8/25/2025 8/28/2025
30 | P17,22 | Alternative Proposals for TO-BE System Configuration and RICEF Development | Regarding the TO-BE system configuration and RICEF development assumptions described in the RFP, would it be possible for us to propose alternative configuration plans or optimized RICEF development approaches if we identify solutions that can more effectively meet your requirements? | 2025-08-25 | Yes, You can, Actually that is exactly what I expect to see. | Hakkie Min Okay Cem | 8/25/2025 8/28/2025
31 | QA record sheet | Cut-over timing | Regarding the cut-over timing, in Q&A, it says “January is OK for cut-over date.” If we cut over earlier than the contract end period (end of March 2027), would an earlier cut-over — the earlier, the better — result in a higher evaluation score? | 2025-08-25 | We cannot say it clearly, But cut over earlier resulted in less overall cost and you can get much better score in "1,Functional Evaluation: and "4.Cost evaluation". Cutover and go live is better on december 1st 2026 or earlier, and avoid year end. Fiscal year end is 2027 March but that has to have the buffer and hyper care. but the evaluations will focus on quality, confidence to deliver and expertise. evalutaion will depend on how best you can convince us you can do that timelines can be part of it and we expect you do deliver what you said you will. cost will be cosideration following cpacity and capability and trustworhines of the vendor, you may want to balance it out. | Hakkie Min Okay Cem | 8/25/2025 8/28/2025
32 | - | Comms & PR Team | From OIST Phase 0 Change Strategy document, we understood that there is a Comms & PR Team, can you if engagement / collaboration from the Project Change Management team with this team is expected? Can we assume that external communications (e.g. vendors, regulartory body) of the project will be managed by Comms & PR Team or OIST team from Procurement and HR | 2025-08-25 | We need to discuss regarding the R&R between "Comms & PR Team" and Change managemen team in project. It is not clearly defined yet but Comms & PR Team will be open to discuss and collaborate. | Hakkie Min | 2025-08-25
33 | Appendix.10 P.49,53 | Change Impact Assessment | According to the leadership interviews, there is a strong need for real-time data analytics to support decision-making across Finance, HR, and Procurement. However, the data to be interfaced with SAC is limited to Finance according to “6. OIST_ToBe System_IF_List_Phase0Assesment,”. Does this mean that SAC wouldn't be implemented for HR and Procurement data in Phase1? | 2025-08-25 | To produce the mandatory reports in OIST, we need not only FInance data but also Procurement and HR data. You should consider to interface the Procuremetn and HR data with SAC. Please itemize these so it can be selectable, we have to validate a real realtime need, in most cases it is unlikely needed when users say they need, want vs need needs to be identified that is the job of a business analyst, i assume you will bring "consultants" who started from business analyst path who would know how to determine real needs. IT will help to some extend. | Hakkie Min Okay Cem | 8/25/2025 8/28/2025
34 | Appendix.7. OIST_ToBe Report_List | SAP Analytics Cloud report target | May I know why some reports (e.g. 消費税の確定申告書：Consumption Tax Return, 源泉徴収票・支払調書(税務署、支払先)：Withholding Tax Certificate and Payment Statement (Tax Office, Payee).) are expected to be implemented in SAP Analytics Cloud? We supposed that these report forms which send to external parties are more sufficient to output via SAP forms, which is also inside "System Scope (To-Be)" in RFP. Do you just require SAP Analytics Cloud to output them in spreadsheet format and users will convert them into design forms manually? | 2025-08-25 | You can propose the best solution. Please consider that there might be two or three types of reports. One that barely changes and can be accomplished by SAP forms, other that eventually needs to be modified or be more flexible, which should be easy to modify by Business Owner or IT staff, and last one that refers ad-hoc reports that could be only possible using SAC. The reports that you refer in your question, fall in the first category. Many of these reprots can be created with SAP forms and it is normal way, and we do that with form we may want to store those in opentext. SAC for the purpose seems an overkill. but you must think of simple and effective ways to achieve the goal with no complexitiesand TCO optimized. please respond with / propose best practices of such reporting as well. | A. Villar Okay Cem | 8/26/2025 8/28/2025
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206